## Sheet1
Task | Priority | Sprint | Ideal Due Date | Finished? | Stretch Goals
Design sanity consequence system | 1 | Jam Pitch Presentation | 2022-02-09 | Yes | Create sprite for enemy type 2 | 3
Design sanity upgrade system | 1 | Jam Pitch Presentation | 2022-02-09 | Yes | Create sprite for enemy type 3 | 3
Design level 1 | 1 | Jam Pitch Presentation | 2022-02-09 | Yes | Create animations for enemy type 2 | 3
Compose main menu theme | 1 | Jam Pitch Presentation | 2022-02-09 | Yes | Create animations for enemy type 3 | 3
Compose general level theme | 1 | Jam Pitch Presentation | 2022-02-09 | Yes | Implement attacks for enemy type 2 | 3
Create game pitch presentation | 1 | Jam Pitch Presentation | 2022-02-16 | WIP | Implement attacks for enemy type 3 | 3
Create main menu UI | 1 | Jam Pitch Presentation | 2022-02-16 | Yes | Create conjured spirit sprite | 3
Create HP UI for enemies | 1 | Jam Pitch Presentation | 2022-02-16 |  | Create conjured spirit animation | 3
Create HP UI for PC | 1 | Jam Pitch Presentation | 2022-02-16 |  | Implement conjured spirit attack | 3
Implement basic attack (close combat): PC -> enemies | 1 | Jam Pitch Presentation | 2022-02-16 |  | Gravestone feature | 3
Implement basic attack (close combat): enemies -> PC | 1 | Jam Pitch Presentation | 2022-02-16
Create sprite for MC | 1 | Jam Pitch Presentation | 2022-02-16 | Yes
Create sprite for enemy type 1 | 1 | Jam Pitch Presentation | 2022-02-16
Create sprite for shrine | 1 | Jam Pitch Presentation | 2022-02-16
Implement win/lose condition per level | 1 | Jam Pitch Presentation | 2022-02-16
Create tiles for passable ground | 1 | Jam Pitch Presentation | 2022-02-16 | Yes
Create exit door tile | 1 | Jam Pitch Presentation | 2022-02-16 | Yes
Create sanity UI for PC | 1 | Jam Pitch Presentation | 2022-02-16
Implement movement for PC | 1 | Jam Pitch Presentation | 2022-02-16
Implement movement for enemies | 1 | Jam Pitch Presentation | 2022-02-16
Create UI for trading sanity for upgrades | 1 | Jam Update Presentation | 2022-02-23
Implement interaction between shrine and character | 1 | Jam Update Presentation | 2022-02-23
Create sprites for columns | 1 | Jam Update Presentation | 2022-02-23
Create tutorial UI | 1 | Jam Update Presentation | 2022-02-23
Begin playtesting | 1 | Jam Update Presentation | 2022-02-23
Compose attack SFX | 1 | Jam Update Presentation | 2022-02-23
Compose player SFX | 2 | Jam Update Presentation | 2022-02-23
Create animations for MC | 1 | Jam Update Presentation | 2022-03-02
Create animations for enemy type 1 | 1 | Jam Update Presentation | 2022-03-02
Create sprite for beloved | 2 | Jam Update Presentation | 2022-03-02
Implement spawner system | 1 | Jam Update Presentation | 2022-03-09
Create animation for beloved | 2 | Jam Update Presentation | 2022-03-09
Create sprite for projectile | 2 | Jam Update Presentation | 2022-03-09
Design remaining levels | 2 | Jam Update Presentation | 2022-03-09
Implement ranged attack: PC -> enemies | 2 | Jam Update Presentation | 2022-03-09
Make design changes based on playtesting feedback | 1 | Jam Demo Day | 2022-03-30
Create sprite for final boss | 2 | Jam Demo Day | 2022-03-30
Create animation for final boss | 2 | Jam Demo Day | 2022-03-30
Design attacks for final boss | 2 | Jam Demo Day | 2022-03-30
Implement attacks for final boss | 2 | Jam Demo Day | 2022-03-30
Compose final boss theme | 2 | Jam Demo Day | 2022-03-30
Compose final boss SFX | 2 | Jam Demo Day | 2022-03-30
Design final boss level | 2 | Jam Demo Day | 2022-03-30